## Sheet1
Requirements | Sprint | Topic | User Story | Task # | Task | Priority | Assigned To | Start Date | End Date | Hours[Task Based] Estimate the testing+development-Technical Panel | StoryPoint[Businessvalue/complexity] Estimates how much we can deliver in a spring+total effort with its tasks with its depencies and other factors[Po+scrum] | Status
| #1 | Admin Registration | As a admin, I want to open admin registration page and save different projects based on skill | Task#1 | Access the homepage | Medium | Chandan | 20/3/19 | 22/3/19 | 2 |  | Done
|  |  |  | Task#2 | Redirect to Admin registration Page | Medium | Sagar | 20/3/19 | 22/3/19 | 5 |  | Done
|  |  |  | Task#3 | Admin Registration Field Validation | Medium | Shubham | 20/3/19 | 22/3/19 | 2 |  | Done
|  | User Registration | As a user, I want to open user registration page and search for different available project | Task#4 | Access the homepage | Medium | Bikash | 25/3/19 | 26/3/19 | 2 |  | Done
|  |  |  | Task#5 | Redirect to UserRegistration Page | Medium | Ashish | 25/3/19 | 26/3/19 | 5 |  | Done
|  |  |  | Task#6 | User Registration Field Validation | Medium | Shubham | 25/3/19 | 28/3/19 | 5 |  | Done
| #2 | View Project | As a user, I want to view different projects ,duration and budget . | Task#7 | Create a view details project where project based on skill are displayed to user | High | Sagar | 27/03/19 | 29/03/19 | 8 |  | Done
| #3 | Update Project | As a admin , I want to update my projects skills | Task#8 | Create a update skill page where admin can update the skill of an existing project | High | Ashish | 28/03/19 | 30/03/19 | 8 |  | Done
|  |  |  | Task#10 | Create freelancer controller class, freelancer DAO class, freelancer entity class and freelancer Service class. | High | Bikash | 25/03/19 | 31/03/19 | 8 |  | Done
|  |  |  | Task#11 | Integrate the code and verify its working. | High | Chandan | 25/03/19 | 31/03/19 | 8 |  | Done
| #4 | Proposal | As a user, I want to send proposal for diferent available project .Admin can accept or reject proposal | Task#12 | Create a view project page where user view diffent project | High | Sagar | 2019-01-04 | 2019-04-04 | 8 |  | Done
|  |  |  | Task#13 | Create a update project page where user can update different skill for project | High | Bikash | 2019-01-04 | 2019-04-04 | 8 |  | Done
|  |  |  | Task#14 | Create a send proposal page where user can send proposal for a different project | High | Shubham | 2019-02-04 | 2019-06-04 | 8 |  | Done
|  |  |  | Task#15 | Create a view proposal page where admin can view proposal sent bu user | High | Ashish | 2019-02-04 | 2019-06-04 | 8 |  | Done
|  |  |  | Task#16 | Modify the freelancer controller,freelancer DAO and freelancer Service class, so that the recorded project is saved in the database | High | chandan | 2019-05-04 | 2019-10-04 | 8 |  | Done
|  |  |  | Task#17 | Integrate the code and verify its working. | High | sagar | 2019-05-04 | 2019-10-04 | 8 |  | Done